## Project status
Sites | Trustee Zones | UPS Replacement Status | DC1 | DC2 | DC3 | DC4 | DC5 | DC6 | DC7 | DC8 | Portables | Required UPS' configured | Ready for Deployment | SNMP v3 Config Status | Delivery Date | Deployment Date | Notes
ELEMENTARY SCHOOLS | [13 empty] | orle
A. Lorne Cassidy | 1 | Done | DC1: 3 | 1 |  |  | UPDATED |  | 2023-03-30
Adrianne Clarkson | 7 | Done | DC1: 3 |  |  |  | UPDATED |  | 2023-04-26
Agincourt PS | 5 | Done | DC1: 3; DC2: 1 | [5 empty] | 2023-08-08
AltaVista PS | 6 | Done | DC1: 3; DC2: 2 | 2 |  |  | UPDATED |  | 2023-05-03
Arch St. PS | 6 | Done | DC1: 2 |  |  |  | UPDATED |  | 2023-05-03
Avalon PS | 8 | Done | DC1: 4; DC2: 1 | 1 |  |  | UPDATED |  | 2023-06-06
Barrhaven PS | 3 | Started | [8 empty] | 1 | YES | YES | bar: DC1 to DC8
Bayshore PS | 4 | Done | DC1: 4 | 1 |  |  |  |  | 2023-06-19
Bayview PS | 11 | Done | DC1: 3 | 2 |  |  | UPDATED |  | 2023-06-08
Bells Corners PS | 5 | Done | DC1: 2 |  |  |  | UPDATED |  | 2023-02-03
Berrigan PS | 3 | Done | DC1: 3; DC2: 2 | 1 |  |  |  |  | 2023-07-25
Blossom Park PS | 11 | Done | DC1: 3; DC2: 1 | 1 |  |  |  |  | 2023-08-02
Briargreen PS | 3 | Done | DC1: 3 | [5 empty] | 2023-08-08
Bridlewood PS | 2 | Done | DC1: 2; DC2: 1 | 1 |  |  |  |  | 2023-08-01
Broadview PS | 10 | Done | DC1: 3; DC2: 2 | 1 |  |  | UPDATED |  | 2023-05-12 | Only 6 UPS are needed, the remaining one UPS will be moved to AY jackson | 6
Cambridge PS | 6 | Done | DC1: 2 |  |  |  | UPDATED |  | 2023-04-26
Carleton Heights PS | 11 | Delivered | DC1: 2 | 2 | YES | YES |  | 2025-03-04 | 2025-03-10
Carson Grove PS | 12 | Done | DC1: 2 | 1 |  |  | UPDATED |  | 2023-02-14
Castlefrank PS | 2 | Done | DC1: 3 | ` |  |  |  |  | 2023-08-04
Castor Valley PS | 7 | Done | DC1: 3 | 2 |  |  | UPDATED |  | 2023-03-01
Cedarview MS | 3 | Done | DC1: 3 | 2 |  |  | UPDATED |  | 2023-03-28
Centennial PS | 10 | Done | DC1: 2 | 1 |  |  |  |  | 2023-06-21
Century PS | Closed | Not Started
Chapman Mills PS | 7 | Done | DC1: 2; DC2: 2 | 1 |  |  |  |  | 2023-07-11
Charles Hulse PS | 6 | Done | DC1: 3 |  |  |  | UPDATED |  | 2023-02-14 | 3 UPS connected to one recepticle, One more receptilce needed
Churchill PS | 10 | Done | DC1: 3 | [5 empty] | 2023-08-09
Clifford Bowey | 11 | Done | DC1: 2 | [5 empty] | 2023-08-10
Connaught PS | 10 | Done | DC1: 3 | [5 empty] | 2023-08-14
Convent Glen ES | 8 | Done | DC1: 2 | [5 empty] | 2023-08-15
Crystal Bay CNTR | 4 | Done | DC1: 2 | 1 |  |  |  |  | 2023-08-24
D. Roy Kennedy PS | 4 | Done | DC1: 2; DC2: 2 |  |  |  | UPDATED |  | 2023-02-15
Devonshire PS | 10 | Done | DC1: 2 | [5 empty] | 2023-08-17
Dunlop PS | 11 | Done | DC1: 2 | [5 empty] | 2023-07-26 | 1 Faulty UPS here to be picked up and replaced
Dunning Foubert ES | 8 | Started | DC1: 2 | 3 | YES | YES |  | 2025-03-05 |  | Power issue at the school, 3 UPS were returned from the school due to power issue
Elgin St. PS | 10 | Done | DC1: 2 | 1 |  |  | UPDATED |  | 2023-04-28
Elmdale PS |  | Done | DC1: 3 | [5 empty] | 2023-08-22
Emily Carr PS | 10 | Done | DC1: 3 | [5 empty] | 2023-07-19
Fallingbrook ES | 8 | Done | DC1: 3 |  |  |  | UPDATED |  | 2023-03-31
Farley Mowat PS | 7 | Done | DC1: 3 | 1 |  |  |  |  | 2023-08-22
Featherston Dr. PS | 6 | Done | DC1: 3; DC2: 1 |  |  |  | UPDATED |  | 2023-03-03
Fielding Dr. PS | 11 | Done | DC1: 3; DC2: 1 | [5 empty] | 2023-08-14
First Ave. PS | 9 | Done | DC1: 2 |  |  |  | UPDATED |  | 2023-05-10
Fisher Park PS | 10 | Done | DC1: 3; DC2: 2 | [5 empty] | 2023-08-02
Forest Valley ES | 12 | Started | DC1: 2 |  | YES | YES
General Vanier PS | 11 | Done | DC1: 2 | [5 empty] | 2023-08-15
Glashan PS | 10 | Done | DC1: 3 | [5 empty] | 2023-08-23
Glen Cairn PS | 2 | Done | DC1: 2 | 1 |  |  |  |  | 2023-08-04
Glen Ogilvie PS | 12 | Done | DC1: 3 | [5 empty] | 2023-07-04 | 2 UPS connected to the recepticle, One UPS is unused. One recepticle is needed
Goulbourn MS | 1 | Done | DC1: 3 | 1 |  |  |  |  | 2023-07-05
Greely PS | 7 | Started | [9 empty] | YES | YES |  |  |  | No recepticle - UPS upgrade has been postponed | bar: DC1 to DC8
Half Moon Bay PS | 3 | Started | DC1: 2; DC2: 1; DC3: 1 | 1 | YES | YES
Hawthorne PS | 6 | Done | DC1: 3; DC2: 2 | [5 empty] | 2023-08-14 | 1 unused UPS in DC1, due to having only 2 recepticle instead of 3
Henry Larsen ES | 12 | Started | [9 empty] | YES | YES |  | 2025-03-05 | bar: DC1 to DC8
Henry Munroe MS | 12 | Done | DC1: 3 | [5 empty] | 2023-07-11 | only one UPS connected to the the recepticle, the two other UPS are still sitting there. Two more receptile needs to installed for the UPS
Heritage PS | 8 | Done | DC1: 3 | [5 empty] | 2023-06-26
Hilson Ave. PS | 10 | Delivered | DC1: 2 |  | YES | YES |  | 2025-03-04 | 2025-03-13
Hopewell Ave. PS | 9 | Done | DC1: 4 |  |  |  | UPDATED |  | 2023-05-12
Huntley Centennial PS | 1 | Done | DC1: 2; DC2: 2 | 1 |  |  | UPDATED |  | 2023-03-17
Jack Donohue PS | 2 | Done | DC1: 3; DC2: 1 | 2 |  |  | UPDATED |  |  | .10-12 & .20
Jockvale ES | 3 | Done | DC1: 3 | [5 empty] | 2023-08-15
John Young ES | 2 | Started | [8 empty] | 1 | YES | YES | bar: DC1 to DC8
Kanata Highlands PS | 2 | Done | DC1: 2; DC2: 1; DC3: 1 |  |  |  | UPDATED |  | 2023-05-15 | .20 not UPDATED
Katimavik ES | 2 | Done | DC1: 2 |  |  |  | UPDATED
Knoxdale PS | 3 | Done | DC1: 3; DC2: 1 |  |  |  | UPDATED |  | 2023-01-31
Lady Evelyn Alt. | 9 | Done | DC1: 3 |  |  |  | UPDATED |  | 2023-05-16
Lakeview PS | 4 | Done | DC1: 4 | 1 |  |  | UPDATED |  | 2023-05-05
LePhare ES | 12 | Done | DC1: 2 | 1 |  |  | UPDATED |  | 2023-03-16
MacSkimming |  | Done | [11 empty] | UPDATED |  | 2023-05-05 | bar: DC1
Manor Park PS | 6 | Started | DC1: 2; DC2: 1 | 1 | YES | YES
Manordale PS | 3 | Not Started | [8 empty] | 1 | bar: DC1 to DC8
Manotick PS | 1 | Done | DC1: 2 | [5 empty] | 2023-08-21
Maple Ridge PS | 8 | Done | DC1: 3 | 1 |  |  |  |  | 2023-06-29
Mary Honeywell PS | 3 | Done | DC1: 3; DC2: 1 | 2 |  |  |  |  | 2023-08-15
Meadowlands PS | 5 | Done | DC1: 3 | 1 |  |  |  |  | 2023-07-20
Metcalfe PS | 7 | Done | DC1: 3 | 1 |  |  | UPDATED |  | 2023-03-16
Mutchmor PS | 9 | Not Started | DC1: 2
North Gower-Marlboro | 1 | Done | DC1: 3 | [5 empty] | 2023-06-28
Orleans Wood PS | 8 | Done | DC1: 3 | [5 empty] | 2023-07-06 | UPS not plugged in due to power
Osgoode PS | 7 | Done | DC1: 2 | 1 |  |  |  |  | 2023-06-27
Pinecrest PS | 5 | Delivered | DC1: 2; DC2: 1 | 2 | YES | YES |  | 2025-03-04 | 2025-03-12
Pleasant Park PS | 6 | Done | DC1: 2; DC2: 1 | 2 |  |  | UPDATED |  | 2023-05-10 | UPS can't be installed on DC2, UPS will be returned to Pleasant Park
Queen Elizabeth PS | 6 | Done | DC1: 3 | [5 empty] | 2023-07-31
Queen Mary St. PS | 6 | Done | DC1: 2 |  |  |  | UPDATED |  | 2023-05-15
Regina St. PS | 4 | Not Started | bar: DC1 to DC8
Richmond PS | 1 | Done | DC1: 2 | 1 |  |  |  |  | 2023-08-03
Rideau Valley Kars MS |  | Done | DC1: 5; DC2: 2 | 1 |  |  |  |  | 2023-07-17 | One faulty UPS to be picked
Riverview Alternate | 6 | Done | [13 empty] | 2023-08-17 | 3 UPS intitally scheduled but only one power outlet in dc1, 2 UPS returned back to parkwood. | bar: DC1
Robert Bateman PS | 11 | Done | DC1: 3; DC2: 1 | [5 empty] | 2023-07-13
Robert E. Wilson PS | 9 | Done | DC1: 2 | [5 empty] | 2023-08-16
Robert Hopkins PS | 12 | Done | DC1: 2 | 1 |  |  |  |  | 2023-07-18
Roberta Bondar PS | 11 | Not Started | DC1: 2
Roch Carrier ES | 2 | Done | DC1: 3 | 1 |  |  | UPDATED |  | 2023-02-08
Rockliffe Park PS | 6 | Not Started | DC1: 2; DC2: 1 | 1
Roland Michner PS | 2 | Not Started | DC1: 2 | 2
Sawmill Creek PS | 11 | Not Started | DC1: 2; DC2: 1 | 1
Severn Ave. PS | 4 | Not Started | DC1: 2 | 1
Sir Winston Chruchill PS | 3 | Not Started | DC1: 2
South March PS | 2 | Not Started | DC1: 2; DC2: 2
Stephen Leacock PS | 2 | Done | DC1: 2 | 1 |  |  |  |  | 2023-08-17
Steve MacLean PS | 7 | Not Started | DC1: 3; DC2: 1 | 2 |  |  |  |  | 2023-10-12
Stittsville PS | 1 | Done | DC1: 3 | 2 |  |  |  |  | 2023-07-24
Stonecrest PS | 1 | Done | DC1: 2; DC2: 2 | 2 |  |  | UPDATED |  | 2023-03-17 | .30 / .21 missed
Summerside PS | 8 | Done | DC1: 3; DC2: 1 | 1 |  |  |  |  | 2023-07-17
Terry Fox ES | 8 | Not Started | DC1: 2
Trillium PS | 8 | Done | DC1: 3 | [5 empty] | 2023-08-10
Vimy Ridge PS | 7 | Not Started | bar: DC1 to DC8
Vincent Massey PS | 6 | Done | DC1: 2; DC2: 1 | [5 empty] | 2023-07-31
Viscount Alexander PS | 9 | Not Started
W.E. Gowling PS | 11 | Not Started
W.E. Johnston PS | 2 | Done | DC1: 3; DC2: 1 | 2 |  |  |  |  | 2023-07-18
W.O. Mitchell ES | 2 | Done | DC1: 3 | 1 |  |  |  |  | 2023-07-19
Westwind PS | 1 | Done | DC1: 4 | 2 |  |  |  |  | 2023-06-22
Woodroffe Ave. PS | 4 | Done | DC1: 3; DC2: 1 | 2 |  |  | UPDATED |  | 2023-02-13 | Yao returned the extra UPS back to Parkwood / portable 372 (.40) but UPS (.30) 2 in dc1 / 1 in dc 2 / 1 in portable
York St. PS | 9 | Done | DC1: 3 |  |  |  | UPDATED |  | 25/5/2023
Albert ST ps |  | Done | DC1: 3; DC2: 2 |  |  |  | UPDATED |  | 2023-06-07 | schedule one level 7 along with Vishal / 2 UPS DC2 not mentioned
SECONDARY SCHOOLS |  | Not Started
A.Y. Jackson SS | 2 | Done | DC1: 3 | 3 |  |  | UPDATED |  | 2023-05-19 | 3 UPS in DC1
Adult HS | 10 | Not Started | DC1: 2; DC2: 2; DC3: 1; DC4: 0
Bell HS | 5 | Done | 3 | 1 | 1 | 1 | 1 |  |  |  | 2 |  |  | UPDATED |  | 2023-02-02
Brookfield HS | 11 | Not Started | DC1: 2; DC2: 1; DC3: 1
Cairine Wilson SS | 8 | Not Started | DC1: 4 | 2
Canterbury HS | 6 | Done | DC1: 3; DC2: /;LKJH¦ | 1 |  |  |  |  | 2023-07-12
Colonel By SS | 12 | Not Started | DC1: 3; DC2: 78908E | 3
Earl of March SS | 2 | Not Started | DC1: 3; DC2: 2; DC3: 1; DC4: 1 | 7
Elizabeth Wyn Wood Sec. Alt | 5 | Done | DC1: 2 | [5 empty] | 2023-08-18
Frederick Banting Sec. Alt. | 1 | Done | DC1: 2 | [5 empty] | 2023-07-25
Glebe C.I. | 9 | Not Started | DC1: 2; DC2: 2; DC3: 2; DC4: 1
Gloucester HS | 12 | Done | 2 | 1 | 1 | 1 |  | 2 |  | 2 |  |  |  | UPDATED |  | 2024-12-30
Hillcrest HS | 6 | Done | DC1: 3; DC2: 2 | 1 |  |  | UPDATED |  | 2023-05-01 | No portable
John McCrae SS | 3 | Not Started | 3 | 1 | 1 | 1 | 1 | 1 |  |  | 4
Lisgar C.I. | 10 | Not Started | DC1: 3; DC2: 1
Longfields-Davidson Heights SS | 3 | Not Started | DC1: 3; DC2: 2; DC3: 1; DC4: 2
Merivale HS | 3 | Not Started | 2 | 2 | 1 | 1 | 1 |  |  |  | 3
Nepean HS | 10 | Not Started | DC1: 3; DC2: 2
Norman Johnston Sec. Alt. | 12 | Done | DC1: 2 | [5 empty] | 2023-07-27
Osgoode Township HS | 7 | Done | DC1: 2 | 4 |  |  | UPDATED |  | 2023-03-16
Ottawa Tech | 6 | Done | DC1: 3; DC2: 1; DC3: 1 | [5 empty] | 2023-07-26
Richard Pfaff Alt. | 10 | Done | DC1: 3 | [5 empty] | 2023-08-17
Ridgemont HS | 6 | Done | DC1: 3; DC2: 2 | 1 |  |  | UPDATED |  | 2023-03-02
Sir Guy Carleton SS | 5 | Delivered | DC1: 2; DC2: 1 |  | YES | YES |  | 2025-03-04 | 2025-03-11
Sir Robert Borden SS | 3 | Not Started | DC1: 3; DC2: 2; DC3: 2; DC4: 1 | 2
Sir Wilfrid Laurier SS | 8 | Done | DC1: 4; DC2: 2 | 1 |  |  | Not Yet |  |  | Wrong Password / Was probably done in the summer
South Carleton SS | 1 | Done | DC1: 3; DC2: 1; DC3: 2; DC4: 2 | 1 |  |  |  |  | 2023-07-10
West Carleton SS | 1 | Done | DC1: 3; DC2: 2; DC3: 1; DC4: 1 | 4 |  |  | UPDATED |  | 2023-02-01 | 1 unused UPS at WCAR located at DC1
Woodroffe HS | 4 | Done | DC1: 3; DC2: 2 | 2 |  |  | UPDATED |  | 2023-02-13 | 2 portables
[11 empty] | School Completed : |  |  | 104
[11 empty] | School Scheduled : |  |  | 0
[11 empty] | School Not Started : |  |  | 29
[11 empty] | UPS currently Deployed : |  |  | 589
[12 empty] | School Started |  | 8
[12 empty] | Total UPS pending to be deployed |  | 156
[12 empty] | Sites Delivered |  | 4

## UPS serial Numbers
Site Code | Serial Number | Model Number | IP ADDRESS | Location
PINE | AS2351154945 | SMX1500RM2UCNC | 10.137.17.10 | DC-1
PINE | AS2352260343 | SMX1500RM2UCNC | 10.137.17.11 | DC-1
PINE | AS2351154972 | SMX1500RM2UCNC | 10.137.17.20 | DC-2
PINE | AS2351154936 | SMX1500RM2UCNC | 10.137.17.30 | Portable
PINE | AS2351154941 | SMX1500RM2UCNC | 10.137.17.40 | Portable
SGCA | AS2351154978 | SMX1500RM2UCNC | 10.186.17.20 | DC-2
SGCA | AS2351154968 | SMX1500RM2UCNC | 10.186.17.10 | DC-1
SGCA | AS2352260347 | SMX1500RM2UCNC | 10.186.17.11 | DC-1
BARR | AS2351154943 | SMX1500RM2UCNC | 10.82.17.20 | Portable
BARR | AS2351154944 | SMX1500RM2UCNC | 10.82.17.30 | Portable
BARR | AS2351154982 | SMX1500RM2UCNC | 10.82.17.10 | DC-1
CHEI | AS2351154940 | SMX1500RM2UCNC | 10.108.17.20 | Portable
CHEI | AS2351154984 | SMX1500RM2UCNC | 10.108.17.30 | Portable
CHEI | AS2351154983 | SMX1500RM2UCNC | 10.108.17.10 | DC-1
CHEI | AS2351154985 | SMX1500RM2UCNC | 10.108.17.11 | DC-1
DUNN | AS2351154937 | SMX1500RM2UCNC | 10.100.17.10 | DC-1
DUNN | AS2351154990 | SMX1500RM2UCNC | 10.100.17.11 | DC-1
DUNN | AS2351154950 | SMX1500RM2UCNC | 10.100.17.20 | Portable
DUNN | AS2351154991 | SMX1500RM2UCNC | 10.100.17.30 | Portable
DUNN | AS2351154981 | SMX1500RM2UCNC | 10.100.17.40 | Portable
FVAL | AS2351154989 | SMX1500RM2UCNC | 10.110.17.10 | DC-1
FVAL | AS2351154993 | SMX1500RM2UCNC | 10.110.17.11 | DC-1
GRLY | AS2351154995 | SMX1500RM2UCNC | 10.116.17.10 | DC-1
HMBA | AS2351264430 | SMX1500RM2UCNC | 10.24.17.10 | DC-1
HMBA | AS2348154818 | SMX1500RM2UCNC | 10.24.17.11 | DC-1
HMBA | AS2348154809 | SMX1500RM2UCNC | 10.24.17.20 | DC-2
HMBA | AS2351154977 | SMX1500RM2UCNC | 10.24.17.30 | DC-3
HMBA | AS2352260103 | SMX1500RM2UCNC | 10.24.17.40 | Portable
HENL | AS2352260104 | SMX1500RM2UCNC | 10.120.17.10 | DC-1
HENL | AS2352260102 | SMX1500RM2UCNC | 10.120.17.20 | DC-2
HILS | AS2351264404 | SMX1500RM2UCNC | 10.49.17.10 | DC-1
HILS | AS2351154929 | SMX1500RM2UCNC | 10.49.17.11 | DC-1
JOHN | AS2351264412 | SMX1500RM2UCNC | 10.126.17.10 | DC-1
JOHN | AS2351154928 | SMX1500RM2UCNC | 10.126.17.20 | Portable
MPAR | AS2351155008 | SMX1500RM2UCNC | 10.74.17.10 | DC-1
MPAR | AS2351264414 | SMX1500RM2UCNC | 10.74.17.20 | DC-1
MPAR | AS2351264369 | SMX1500RM2UCNC | 10.74.17.30 | DC-2
MPAR | AS2351264351 | SMX1500RM2UCNC | 10.74.17.40 | Portable

## Schools Contacts
Site Code | Principal | VP-1 | VP-2 | AO | Chief custodian
BARR | Sue Christie |  |  | Nicole Kingsbury | Glen Balson
CHEI | Lakesha Young | Pascale Evans |  | Tiffany Jones | Ruggiero D'Amato
DUNN | Robert Levesque | Trent Clark |  | Lisa Burton
FVAL | Rebecca Ryan |  |  | Katherine Partington | Stephen Mondey
GRLY | Robert Richardson |  |  | Rachael Bennett | Patricia Messervey
HMBY | Chris Toivonen | Allison Hunter Slack |  | Jane Foster | Justin Disipio
HENL | Kati Mackie | Jenna Anderson |  | Rose Sharpe | Jesse Larabie
HILS | Alisa Viner | Christol Barrett |  | Liane Armstrong | Daniel Weber
JOHN | Kimberly Simpson | Kristine Storah |  | Karen Hall Dafoe | Josh Gordon
MPAR | Richie Dosanjh | Lisa Potter |  | Carrie Foley | Andrew Cornforth
MAND | Lisa Langill | Ainsley Hughes |  | Shelley Valadares | Alex Dean
PINE | Naya Markanastasakis | Nivin Radwan |  | Angelita Stolarik | Gemma Gloriani
SGCA | Dori-Anne Marcelin | Christine Reynolds | Igor Tesanovic | Brenda Tanner | Todd Lafleur

## school with issues
| School | Issues | Status | Notes
1 | Arch St. PS | DC2 UPS can't be replaced because rack is wall mounted | Pending
2 | Broadview PS | Only 6 UPS are needed, the remaining one UPS will be moved to AY jackson | Resolved | might need a site visit
3 | Glen Ogilvie PS | 2 UPS connected to the recepticle, One UPS is unused. One recepticle is needed | Pending | Unused UPS needs to be picked up
4 | Goulbourn MS | Two more UPS needed here | Pending | 1 more UPS needed for DC1 and 1 for portable
5 | Henry Munroe MS | only one UPS connected to the the recepticle, the two other UPS are still sitting there. Two more receptile needs to installed for the UPS | Pending | 2 ups to be picke up
6 | Jack Donohue PS | .10-12 & .20 | Pending | Needs site visit to confirm UPS in portable, 2 portable moved to Earl of march, site visit to earl of march is needed
7 | Kanata Highlands PS | .20 not UPDATED | Resolved
8 | Pleasant Park PS | UPS can't be installed on DC2, UPS will be returned to Pleasant Park | Pending | site visit required, not sure what is going at gthe school
9 | Rideau Valley Kars MS | One new UPS needs to be picked, 3 old UPS to be picked | Resolved
10 | Stonecrest PS | .30 / .21 missed | Pending | network card to be replaced
11 | Woodroffe Ave. PS | Yao returned the extra UPS back to Parkwood / portable 372 (.40) but UPS (.30) 2 in dc1 / 1 in dc 2 / 1 in portable | Pending | Site visit required to confirm if both portables have new UPS
12 | York St. PS |  | Resolved
13 | Albert ST ps | schedule one level 7 along with Vishal / 2 UPS DC2 not mentioned | Resolved
14 | A.Y. Jackson SS | 3 UPS in DC1 | Resolved
15 | Hillcrest HS | No portable | Pending | Site visit required for one unused UPS
16 | Woodroffe HS | 2 portables | Resolved
17 | Bayshore PS | requires two extra UPS, 1 UPS for portable, 1 UPS to replace another faulty one in DC1, | Pending | Need to schedule a time to replace UPS
18 | Westwind PS |  | Pending | faulty UPS still under investigation
19 | Maple Ridge | power issue at Maple ridge, Old UPS needs to used until the power is restored at the school. | Pending | Vishal working on fixing two fault UPS there
20 | ORLW | Possible power issue between 6:30 am till 7:30 Pm that affect UPS to get online frequently | Pending | Asked custodian to reach facilities to check power lines. 3 old ups replaced temporary
21 |  |  | Pending
22 |  |  | Pending

## Schools to be revisted
School | Issues | Quantity | Status | Notes | Team member assigned
Dunlop PS | Faulty UPS to be picked up | 2 | pending | Faulty UPS should be replaced / 1 fualty Unit / 1 with P0.5 error (.10 & .11) | Vishal
Glen Ogilvie PS | Unused UPS to be picked up | 1 | resolved | Richard assigned to do it | Richard
Henry Munroe | Unused UPS to be picked up | 2 | resolved | Richard assign do it | Richard
Goulborn MS | More UPS needed | 2 | resolved | Richard delivered, configured and installed 2 extra UPS | Richard
Hillcrest HS | Unused UPS to be picked up | 1 | pending | Richard assigned to do it
Summerside | Faulty UPS to be picked up | 1 | pending | Faulty UPS at DC2 replaced with old UPS, need replacement
Kars on Rideau | Faulty UPS to be picked up | 1 | resolved |  | Richard
Robert Bateman | Faulty UPS to be picked up | 1 | resolved | 1 Faulty UPS at DC1 Replaced, Need to pickup from school
Frederick Banting | Faulty UPS to be picked up | 1 | resolved | 1 Faulty UPS at DC1 Need replacement (.11) | Richard
Maple Ridge | Faulty UPS to be picked up | 1 | resolved | Richard needs to return to two faulty UPs back to park | Richard | one of the faulty UPS to be returned has a new battery iin it
W.E. Johnnston | Faulty UPS to be picked up | 1 | resolved | 1 Faulty UPS at Portable need replacement (.40) | Richard
Robert Hopkins | Faulty UPS to be picked up | 1 | resolved | 1 Faulty UPS at DC1 (.11) | Richard
Hawthorne | Unused UPS to be picked up | 1 | resolved | 1 used UPS in DC1, due to having only 2 recepticle instead of 3 | Richard
Briagreen PS | Faulty UPS to be picked up | 1 | pending | 1 Faulty UPS at DC1 need replace
Richard Pfaff Secondary Alt | Faulty UPS to be picked up | 2 | resolved |  | Melvin
General Vanier | Faulty UPS to be picked up | 1 | pending
Farley Mowatt | Faulty UPS to be picked up | 1 | resolved |  | Richard
Mary Honeywell | Faulty UPS to be picked up | 1 | resolved | faulty UPS replaced with one unused UPS at DC1 Need to pickup old and faulty UPS/ DC1 may need one UPS after wifi2 project | Vishal
Agincourt | Faulty UPS to be picked up | 1 | resolved |  | Vishal
FDRI | Faulty UPS to be picked up | 1 | resolved | Faulty UPS at DC2 to be replaced, Vissha assigned to work on this | Vishal
BAYS | More UPS needed | 2 | pending | 1 Faulty UPS at DC1 / 1 UPS need for portable

## Old UPS to be picked up
Pick Up Status
1 | A. Lorne Cassidy | Picked Up | A. Lorne Cassidy | A. Lorne Cassidy
2 | Adrianne Clarkson | Picked Up | Adrianne Clarkson | Adrianne Clarkson
3 | AltaVista PS | Picked Up | Bayshore PS | #N/A
4 | Cambridge PS | Picked Up | Bayview PS | Bayview PS
5 | Castor Valley PS | Picked Up | Bells Corners PS | Bells Corners PS
6 | Cedarview MS | Picked Up | Berrigan PS | #N/A
7 | Elgin St. PS | Picked Up | Blossom Park PS | Blossom Park PS
8 | Fallingbrook ES | Picked Up | Briargreen PS | Briargreen PS
9 | Featherston Dr. PS | Picked Up | Bridlewood PS | #N/A
10 | Huntley Centennial PS | Picked Up | Cambridge PS | Cambridge PS
11 | Metcalfe PS | Picked Up | Carson Grove PS | Carson Grove PS
12 | Roch Carrier ES | Picked Up | Castlefrank PS | #N/A
13 | Stonecrest PS | Picked Up | Castor Valley PS | Castor Valley PS
14 | Bell HS | Picked Up | Cedarview MS | Cedarview MS
15 | Osgoode Township HS | Picked Up | Centennial PS | #N/A
16 | Ridgemont HS | Picked Up | Chapman Mills PS | #N/A
17 | Sir Wilfrid Laurier SS | Picked Up | Charles Hulse PS | Charles Hulse PS
18 | Woodroffe HS | Picked Up | Churchill PS | Churchill PS
19 | Lakeview PS | Picked Up | Clifford Bowey | Clifford Bowey
20 | Avalon PS | Picked Up | Connaught PS | #N/A
21 | Bayview PS | Picked Up | Convent Glen ES | #N/A
22 | Bells Corners PS | Picked Up | D. Roy Kennedy PS | D. Roy Kennedy PS
23 | Carson Grove PS | Picked Up | Devonshire PS | #N/A
24 | Charles Hulse PS | Picked Up | Elgin St. PS | Elgin St. PS
25 | D. Roy Kennedy PS | Picked Up | Elmdale PS | #N/A
26 | First Ave. PS | Picked Up | Emily Carr PS | #N/A
27 | Hopewell Ave. PS | Picked Up | Fallingbrook ES | Fallingbrook ES
28 | Kanata Highlands PS | Picked Up | Farley Mowat PS | #N/A
29 | Katimavik ES | Picked Up | Featherston Dr. PS | Featherston Dr. PS
30 | Knoxdale PS | Picked Up | Fielding Dr. PS | #N/A
31 | Lady Evelyn Alt. | Picked Up | First Ave. PS | First Ave. PS
32 | LePhare ES | Picked Up | Fisher Park PS | #N/A
33 | Queen Mary St. PS | Picked Up | General Vanier PS | #N/A
34 | Roch Carrier ES | Picked Up | Glen Cairn PS | #N/A
35 | Stonecrest PS | Picked Up | Goulbourn MS | #N/A
36 | York St. PS | Picked Up | Heritage PS | #N/A
37 | Albert ST ps | Picked Up | Hopewell Ave. PS | Hopewell Ave. PS
38 | A.Y. Jackson SS | Picked Up | Huntley Centennial PS | Huntley Centennial PS
39 | Bell HS | Picked Up | Jockvale ES | #N/A
40 | Hillcrest HS | Picked Up | Katimavik ES | Katimavik ES
41 | Osgoode Township HS | Picked Up | Knoxdale PS | Knoxdale PS
42 | West Carleton SS | Picked Up | Lady Evelyn Alt. | Lady Evelyn Alt.
43 | Blossom Park PS | Picked Up | Lakeview PS | Lakeview PS
44 | Briargreen PS | Picked Up | LePhare ES | LePhare ES
45 | Churchill PS | Picked Up | MacSkimming | #N/A
46 | Clifford Bowey | Picked Up | Manotick PS | #N/A
47 | Glashan | Picked Up | Maple Ridge PS | #N/A
|  |  | Mary Honeywell PS | #N/A
|  |  | Metcalfe PS | Metcalfe PS
|  |  | North Gower-Marlboro | #N/A
|  |  | Orleans Wood PS | #N/A
|  |  | Osgoode PS | #N/A
|  |  | Queen Mary St. PS | Queen Mary St. PS
|  |  | Robert Bateman PS | #N/A
|  |  | Robert E. Wilson PS | #N/A
|  |  | Robert Hopkins PS | #N/A
|  |  | Roch Carrier ES | Roch Carrier ES
|  |  | Stephen Leacock PS | #N/A
|  |  | Stittsville PS | #N/A
|  |  | Trillium PS | #N/A
|  |  | Vincent Massey PS | #N/A
|  |  | W.E. Johnston PS | #N/A
|  |  | W.O. Mitchell ES | #N/A
|  |  | Westwind PS | #N/A
|  |  | Bell HS | Bell HS
|  |  | Canterbury HS | #N/A
|  |  | Elizabeth Wyn Wood Sec. Alt | #N/A
|  |  | Osgoode Township HS | Osgoode Township HS
|  |  | Ottawa Tech | #N/A
|  |  | Richard Pfaff Alt. | #N/A
|  |  | Ridgemont HS | Ridgemont HS
|  |  | Sir Wilfrid Laurier SS | Sir Wilfrid Laurier SS
|  |  | South Carleton SS | #N/A
|  |  | West Carleton SS | West Carleton SS
|  |  | Arch St. PS | #N/A
|  |  | Broadview PS | #N/A
|  |  | Dunlop PS | #N/A
|  |  | Dunning Foubert ES | #N/A
|  |  | Glen Ogilvie PS | #N/A
|  |  | Greely PS | #N/A
|  |  | Hawthorne PS | #N/A
|  |  | Henry Munroe MS | #N/A
|  |  | Jack Donohue PS | #N/A
|  |  | Kanata Highlands PS | Kanata Highlands PS
|  |  | Pleasant Park PS | #N/A
|  |  | Rideau Valley Kars MS | #N/A
|  |  | Stonecrest PS | Stonecrest PS
|  |  | Woodroffe Ave. PS | #N/A
|  |  | York St. PS | York St. PS
|  |  | Albert ST ps | Albert ST ps
|  |  | A.Y. Jackson SS | A.Y. Jackson SS
|  |  | Hillcrest HS | Hillcrest HS
|  |  | Woodroffe HS | Woodroffe HS
|  |  | Glashan | Glashan